Agent Ops & Governance Platform Foundation

- BACKGROUND & OBJECTIVES:

Brightspeed currently operates a growing number of independent, team-level AI agent experiments. This has produced inconsistent prompts and instructions, hidden token usage and cost, point-to-point application integrations, and an absence of standard governance. Without a common platform layer, each new agent adds risk, duplication, and operational overhead rather than compounding value across the enterprise.

The engagement establishes a governed, GCP-native Agent Ops & Governance Platform — a control plane through which all future agents are registered, assessed, deployed, accessed, and reviewed. The goal is not to build standalone agents, but to create the common platform layer through which every future agent is governed, costed, and scaled.

Strategic Objectives

- Move Brightspeed from fragmented, team-level agent experimentation to a governed, enterprise-wide platform foundation.

- Establish a GCP-native, platform-agnostic control plane that onboards, governs, evaluates, monitors, and scales every future agent.

- Enable a hub-and-spoke operating model in which teams build locally and promote agents centrally, aligned with enterprise governance standards.

- Create a reusable enterprise AgentOps foundation that reduces the cost and risk of onboarding future agents at scale.

Operational Objectives

- Design and implement a target architecture, IAM model, and runtime strategy on GCP for enterprise agent deployment.

- Build the core platform components: agent registry, onboarding layer, prompt & instruction repository, workflow/orchestration layer, governance & HITL control layer, and evaluation layer.

- Onboard and validate one new agent and one existing agent (reference agents) end-to-end through the platform, including governance, evaluation, telemetry, and cost tracking.

- Deliver enterprise readiness assets — a FinOps cost model, deployment templates, an AI-DLC operating model, and runbooks — to support Day-2 operations and Phase 2 scale-up.

- SCOPE:

The Agent Ops & Governance Platform will be built as a GCP-native, platform-agnostic control plane, deployed within Brightspeed’s GCP environment.

90-Day Delivery — Implementation Waves

The engagement is structured across four implementation waves over a 12-week build period, followed by 4 weeks of post go-live support.

Wave 1 — Platform Foundation (Weeks 1–2)

- Define the target architecture, IAM model, and runtime strategy on GCP.

- Select the reference agent(s) for onboarding in Wave 3.

Wave 2 — Core Platform Components (Weeks 3–8)

- Build the Agent Registry: schema, metadata model, lifecycle states, versioning, and risk-tiering fields.

- Build the Agent Onboarding Layer: intake forms, API contracts, artifact assessment checklist, and onboarding gates.

- Build the Prompt & Instruction Repository: golden prompt templates, instruction standards, versioning, and approval workflow.

- Build the Workflow & Orchestration Layer: workflow design patterns, orchestration templates, sub-agent patterns, and reusable reference flows.

- Build the Governance & HITL Control Layer: governance operating model, approval gates, audit requirements, policy controls, and risk-tiering rules.

- Build the Evaluation Layer: evaluation packs, test case registry, evidence templates, acceptance criteria, and promotion thresholds.

Wave 3 — Reference Agent Onboarding (Weeks 9–11)

- Build and onboard one new agent end-to-end on the platform (intent capture → workflow configuration → evaluation → governance → deployment → monitoring).

- Onboard one existing agent by reconstructing its workflow within the platform and aligning it to enterprise prompt, tool, and governance standards.

- Validate governance and monitoring live for both reference agents.

Wave 4 — Enterprise Readiness (Week 12)

- Finalize the FinOps cost model and deployment templates.

- Document the AI-DLC operating model, RACI, and Day-2 operations runbooks.

- Deliver an implementation-ready roadmap and backlog for Phase 2 scale-up.

Platform Component Framework

The platform comprises eleven components, each mapped to a corresponding GCP-native service.

| # | Platform Component | What Will Be Defined / Built | GCP-Native Mapping |
| --- | --- | --- | --- |
| 1 | Agent Registry | Registry schema, ownership, metadata model, lifecycle states, versioning, risk-tiering fields, approval status | BigQuery / Cloud SQL / Firestore, UI dashboard |
| 2 | Agent Onboarding Layer | Onboarding intake forms, API contracts, artifact assessment checklist, onboarding gates | API Gateway, Cloud Run / GKE |
| 3 | Workflow & Orchestration Layer | Workflow design patterns, orchestration templates, sub-agent patterns, reusable reference flows | Vertex AI capabilities |
| 4 | Prompt & Instruction Repo | Golden prompt templates, instruction standards, approval workflow, versioning | GitHub for prompt versioning |
| 5 | Tool Registry & MCP Connectivity | Tool schema, tool approval process, MCP connector pattern, access model | Agent Registry/Gateway |
| 6 | A2A-Ready Communication Layer | A2A-ready contracts, agent cards, interaction model, handoff patterns | A2A protocol, Agent Cards, Agent Runtime/Agent Engine |
| 7 | Evaluation Layer | Evaluation packs, test case registry, evidence templates, acceptance criteria, promotion thresholds | Vertex AI Agent Platform |
| 8 | Governance & HITL Control Layer | Governance operating model, approval gates, audit requirements, policy controls, risk-tiering rules | Cloud Audit Logs and governance tooling |
| 9 | Deployment & API Exposure Layer | Deployment patterns, API exposure model, promotion gates, rollback approach, access controls | Cloud Run/GKE, API Gateway, Cloud Deploy/Build, IAM and Secret Manager |
| 10 | Observability & FinOps Layer | Telemetry schema, alerting, usage tracking, token/model cost tracking, cost allocation, agent cost marketplace model | Cloud Monitoring, Cloud Trace, billing exports |
| 11 | AI-DLC Operating Model | AI-DLC lifecycle, roles, RACI, GitHub Issue orchestration, evidence pack, hub-and-spoke model | GitHub issue orchestration, Jira integration |

Onboarding Paths

The platform supports two onboarding paths for current and future agents:

- New Agent Creation — Business intent is converted into a production-ready agent through a standardized, governed lifecycle: intent capture, agent work package, registration, workflow configuration (tools/MCP, orchestration, A2A readiness), evaluation and approval, and deployment/monitoring.

- Existing Agent Onboarding — Existing agents are inventoried, their prompts/tools/logic are standardized to enterprise patterns, the workflow is rebuilt inside the platform, and the agent is evaluated, governed, registered, deployed, and monitored centrally.

In-Scope Deliverables (Summary)

- Target architecture and GCP-native mapping

- Governance and operating model

- Monitoring / FinOps model

- Reference agent onboarding (one new, one existing)

- Roadmap & backlog for Phase 2 scale-up

Base Scope Boundaries & Dependency-Driven Constraints

| Boundary / Constraint | Why This Boundary Exists | Recommended Treatment |
| --- | --- | --- |
| Will not duplicate the existing AI-DLC agent development workstream | Duplicate agent builds would create overlap and confusion | Treat the existing workstream as the first onboarding/integration proof for the central platform |
| Will not depend on broad Gemini Enterprise licensing | Broad Gemini Enterprise licenses are not currently being provisioned | Use an API-first, Vertex AI / GCP-native architecture; keep Gemini Enterprise as optional future compatibility |
| Will not assume OpenAI API usage | OpenAI API has not been approved by Brightspeed security | Use Brightspeed-approved GCP / Vertex AI patterns unless security approvals change |
| Will not enable autonomous writes or workflow execution in the base phase | First phase should remain assisted/advisory with human approval | Allow summarize, draft, recommend, classify, validate, and produce evidence; block autonomous writes |
| Will not production-integrate every internal application or connector in 90 days | Internal app connectivity requires security, data access, API readiness, and owner availability | Define MCP strategy and build one priority reference connector pattern; backlog the rest |
| Will not guarantee infrastructure deployment timelines if GCP/security approvals are delayed | Brightspeed-owned access, IAM, security, and project provisioning are dependencies | Produce implementation-ready patterns and use sandbox/mock/stub approaches until access is approved |
| Will not commit to final platform OpEx without usage assumptions | Cost depends on model choice, token volume, request volume, logging retention, runtime, connectors, evaluation frequency | Provide an OpEx calculator with assumptions and cost-control levers |
| Will not replace systems of record | Jira, GitHub, Confluence, ServiceNow, MDR, CCAI, and BigQuery remain authoritative systems | Integrate through APIs/connectors and maintain evidence in approved systems |
| Will not roll out enterprise-wide adoption in the base 90-day scope | First phase should establish the platform and enable one controlled IT onboarding path | Provide change management and rollout roadmap as next-phase work |
| Will only use agents available within Vertex AI, not external agent frameworks | Keeps the platform on the Brightspeed-approved, GCP-native, security-reviewed stack | Build/select agents using Vertex AI (Agent Builder, Agent Engine, ADK); evaluate external frameworks only as separately-approved future options |
| Will not build a separate user management or identity store | Enterprise identity must stay centrally governed | Integrate with Brightspeed SSO / IdP (Cloud Identity / IAM); no bespoke authentication |
| Will build on Google-native serverless services, not self-managed infrastructure | Serverless provides scalability, pay-per-use cost, lower operational overhead, faster delivery | Use Cloud Run / Cloud Functions / Workflows and managed GCP services |
| Will install and configure MCP servers only; building new MCP servers is out of scope | Custom MCP server development is a larger build with additional security, ownership, and maintenance implications | Install/configure approved/existing MCP servers and connectors; backlog custom MCP server creation |

- DELIVERABLES:

The following deliverables will be produced across the four delivery waves of the engagement.

| # | Deliverable | Description | Week |
| --- | --- | --- | --- |
| 1.1 | Target Architecture & GCP-Native Mapping | GCP-native target architecture, environment model, IAM/service account assumptions, runtime decision log, security assumptions | 2 |
| 1.2 | Architecture Decision Log & Platform Backlog | Documented architecture decisions and an initial platform backlog | 2 |
| 2.1 | Agent Registry (Schema, Metadata, Lifecycle) | Registry schema, metadata model, lifecycle states, risk-tiering fields | 8 |
| 2.2 | Prompt & Instruction Repository | Golden prompt templates, instruction standards, versioning and approval workflow | 8 |
| 2.3 | Workflow & Orchestration Templates | Reusable workflow/orchestration templates, sub-agent patterns, A2A-ready handoff pattern | 8 |
| 2.4 | Governance & HITL Control Framework | Risk-tiering model, approval gates, audit requirements, policy controls, exception process | 8 |
| 2.5 | Evaluation Pack v1 | Golden prompt test cases, evaluation scorecards, acceptance criteria | 8 |
| 3.1 | Reference Agent — New | One new agent built end-to-end on the platform with governance, evaluation, and monitoring | 11 |
| 3.2 | Reference Agent — Existing Onboarding | One existing agent onboarded and standardized on the platform | 11 |
| 3.3 | Tool Registry & MCP Connector Design | Tool schema, permission matrix, and MCP connector pattern for the priority reference connector | 11 |
| 4.1 | Observability & FinOps Dashboard | Telemetry schema, usage/cost dashboards, token/model tracking, cost labels, budget/quota model | 12 |
| 4.2 | Deployment Templates & Runbooks | Deployment/promotion/rollback templates, AI-DLC operating model, RACI, Day-2 runbooks | 12 |
| 4.3 | Phase 2 Roadmap & Backlog | Implementation-ready roadmap and backlog for scale-up | 12 |

- TIMELINE & MILESTONES:

Term:

The SOW Term (“Term”) shall begin on Aug 3, 2026 and end on Dec 18,2026. The proposal defines the schedule only in relative weeks (Week 1–Week 16 including post go-live support).

| Wave / Activity | Weeks |
| --- | --- |
| Wave 1 — Platform Foundation | 1–2 |
| Wave 2 — Core Platform Components | 3–8 |
| Wave 3 — Reference Agent Onboarding | 9–11 |
| Wave 4 — Enterprise Readiness | 12 |
| Post Go-Live Support (included) | 13–16 |

- DELIVERY STANDARDS:

Acceptance Criteria:

| Area | Acceptance Criteria |
| --- | --- |
| Architecture | Target architecture is future-proof and demonstrates fulfilling all requirements; reviewed and accepted by Brightspeed stakeholders |
| Runtime | Reference runtime/API pattern demonstrated or implementation-ready |
| Governance | Risk-tiering, intake, approval gates, and exception process documented |
| Prompt / Evaluation | Golden prompts, refusal tests, data-boundary tests framework created |
| MCP | Internal connectivity strategy and priority connector model defined |
| Existing workstream integration | Onboarding path for the existing AI-DLC / E2E testing workstream documented (1 Agent) |
| Observability | Usage, token, model, cost, latency, tool-call, and exception telemetry model defined |
| Operating model | Hub-and-spoke model and RACI completed |
| Roadmap | Next 90-day (Phase 2) roadmap created for decision |